## Gantt Chart
[48 empty] | SCHOOL HOLIDAYS |  |  |  |  | SCHOOL HOLIDAYS |  |  |  |  | SCHOOL HOLIDAYS
| Task | 2025-05-02 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22
Phase 1: Preliminary
1 | Initial Project Proposal
# | Find client
# | Decide on project
# | Write proposal
@ | Complete Proposal
@ | Submit Proposal
2 | Gantt chart
# | Identify tasks
# | Set task duration
# | Identify task milestones
# | Create & format Gantt chart
@ | Submit Gantt chart
Phase 2: Analysis
1 | Data Collection
# | Decide on 2 data collection methods
# | Prepare interview questions
# | Conduct audio interview with client
# | Document transcript of conversation
# | Prepare survey questions
# | Conduct survey with client
# | Print out survey results
@ | Submit data collection
2 | Analytical tools
# | Create use-case diagram
# | Create context diagram
# | Create data-flow diagram
@ | Submit analytical tools
3 | SRS
# | Identify functional and non-functional requirements
# | Identify any constraints
# | Describe scope
# | Describe technical environment
# | Describe intended audience
# | Document Creative & Critical thinking process of SRS
# | Review SRS
@ | Submit SRS
Phase 3: Design
1 | Initial Design Folio
# | Develop initial design ideas through ideation techniques
# | Design 3 draft mock-ups
# | Annotate design idea creations
# | Prepare evaluation criteria
# | Develop three design ideas
# | Evaluate design ideas with evaluation criteria
# | Further develop chosen idea
2 | Detailed Designs
# | Completed finale mockups of all required user interfaces
# | List design principles
# | Annotate final mockups
# | Create data dictionary
# | Create pseudocode to document main logic of several modules
# | Create Object Descriptions
# | Create IPO charts of several modules
# | Document critical & creative thinking process
# | Evaluate and finalise designs
@ | Submit Designs
Phase 4: Development
1 | Software Solution
# | Construct user interface
# | Code solution
# | Create external files
# | Test solution
# | Internal documentation
2 | Alpha Testing
# | Prepare test
# | Conduct tests
# | Document debugging process
# | Document results and proposed modifications
@ | Submit Alpha Testing report
3 | Beta Testing
# | Prepare beta testing plan
# | Conduct beta tests with selected clients/users
# | Document results and proposed modifications
@ | Submit Beta Testing report
Phase 5: Evaluation
1 | Evaluation Strategy and Report
# | Prepare evaluation strategies
# | Complete solution evaluation
# | Document evaluation findings
2 | Assessment of project plan
# | Adjust original Gantt chart
# | Provide annotations for each change
# | Document effectiveness of Gantt chart