## Project Log
| Project Start Date |  | 2025-05-02
| Project End Date |  | 2025-08-21
| Total Duration |  | 112
Task | Start Date | End Date | Duration
Phase 1: Preliminary
Initial Project Proposal
Find client | 2025-05-02 | 2025-05-02 | 1
Decide on project | 2025-05-05 | 2025-05-06 | 2
Write proposal | 2025-05-07 | 2025-05-09 | 3
Complete Proposal | 2025-05-09 | 2025-05-09 | 1
Submit Proposal | 2025-05-12 | 2025-05-12 | 1
Gantt chart
Identify tasks | 2025-05-05 | 2025-05-06 | 2
Set task duration | 2025-05-06 | 2025-05-07 | 2
Identify task milestones | 2025-05-07 | 2025-05-08 | 2
Create & format Gantt chart | 2025-05-07 | 2025-05-08 | 2
Submit Gantt chart | 2025-05-12 | 2025-05-12 | 1
Phase 2: Analysis
Data Collection
Decide on 2 data collection methods | 2025-05-12 | 2025-05-13 | 2
Prepare interview questions | 2025-05-14 | 2025-05-16 | 3
Conduct audio interview with client | 2025-05-19 | 2025-05-20 | 2
Document transcript of conversation | 2025-05-21 | 2025-05-21 | 1
Prepare survey questions | 2025-05-19 | 2025-05-19 | 1
Conduct survey with client | 2025-05-20 | 2025-05-21 | 2
Print out survey results | 2025-05-22 | 2025-05-22 | 1
Submit data collection | 2025-05-23 | 2025-05-23 | 1
Analytical tools
Create use-case diagram | 2025-05-14 | 2025-05-16 | 3
Create context diagram | 2025-05-19 | 2025-05-20 | 2
Create data-flow diagram | 2025-05-21 | 2025-05-23 | 3
Submit analytical tools | 2025-05-23 | 2025-05-23 | 1
SRS
Identify functional and non-functional requirements | 2025-05-12 | 2025-05-13 | 2
Identify any constraints | 2025-05-14 | 2025-05-16 | 3
Describe scope | 2025-05-19 | 2025-05-21 | 3
Describe technical environment | 2025-05-22 | 2025-05-23 | 2
Describe intended audience | 2025-05-26 | 2025-05-27 | 2
Document Creative & Critical thinking process of SRS | 2025-05-28 | 2025-05-29 | 2
Review SRS | 2025-05-30 | 2025-05-30 | 1
Submit SRS | 2025-05-30 | 2025-05-30 | 1
Phase 3: Design
Initial Design Folio
Develop initial design ideas through ideation techniques | 2025-05-26 | 2025-05-28 | 3
Design 3 draft mock-ups | 2025-05-29 | 2025-06-02 | 5
Annotate design idea creations | 2025-06-03 | 2025-06-04 | 2
Prepare evaluation criteria | 2025-06-05 | 2025-06-05 | 1
Develop three design ideas | 2025-06-06 | 2025-06-09 | 4
Evaluate design ideas with evaluation criteria | 2025-06-10 | 2025-06-10 | 1
Further develop chosen idea | 2025-06-11 | 2025-06-11 | 1
Detailed Designs
Completed finale mockups of all required user interfaces | 2025-06-12 | 2025-06-12 | 1
List design principles | 2025-06-13 | 2025-06-13 | 1
Annotate final mockups | 2025-06-16 | 2025-06-17 | 2
Create data dictionary | 2025-06-17 | 2025-06-17 | 1
Create pseudocode to document main logic of several modules | 2025-06-18 | 2025-06-18 | 1
Create Object Descriptions | 2025-06-18 | 2025-06-18 | 1
Create IPO charts of several modules | 2025-06-19 | 2025-06-19 | 1
Document critical & creative thinking process | 2025-06-12 | 2025-06-23 | 12
Evaluate and finalise designs | 2025-06-23 | 2025-06-26 | 4
Submit Designs | 2025-06-27 | 2025-06-27 | 1
Phase 4: Development
Software Solution
Construct user interface | 2025-07-16 | 2025-07-19 | 4
Code solution | 2025-07-20 | 2025-07-31 | 12
Create external files | 2025-07-27 | 2025-08-04 | 9
Test solution | 2025-08-01 | 2025-08-06 | 6
Internal documentation | 2025-07-23 | 2025-08-08 | 17
Alpha Testing
Prepare test | 2025-06-30 | 2025-07-28 | 29
Conduct tests | 2025-07-29 | 2025-08-04 | 7
Document debugging process | 2025-08-01 | 2025-08-06 | 6
Document results and proposed modifications | 2025-08-06 | 2025-08-12 | 7
Submit Alpha Testing report | 2025-08-15 | 2025-08-15 | 1
Beta Testing
Prepare beta testing plan | 2025-08-06 | 2025-08-08 | 3
Conduct beta tests with selected clients/users | 2025-08-11 | 2025-08-14 | 4
Document results and proposed modifications | 2025-08-15 | 2025-08-19 | 5
Submit Beta Testing report | 2025-08-22 | 2025-08-22 | 1
Phase 5: Evaluation
Evaluation Strategy and Report
Prepare evaluation strategies | 2025-08-08 | 2025-08-13 | 6
Complete solution evaluation | 2025-08-14 | 2025-08-18 | 5
Document evaluation findings | 2025-08-19 | 2025-08-21 | 3
Assessment of project plan
Adjust original Gantt chart | 2025-08-12 | 2025-08-14 | 3
Provide annotations for each change | 2025-08-15 | 2025-08-18 | 4
Document effectiveness of Gantt chart | 2025-08-19 | 2025-08-21 | 3